## Sheet1
Key | Folder | Parent Task |  | Title | Status | Priority | Start - End | Assigned To |  |  |  |  | Description
1 | / | Planning |  | Create Project Plan | Complete | Done | 9/14 - 9/21 | Amanda | Connor | Ethan | Jhet | Nathan | Begin Phase 1 [PLANNING]
2 | / | Planning |  | Team Roles Assignment | Complete | Done | 9/21 - 9/28 | Amanda | Connor | Ethan | Jhet | Nathan
3 | / | Planning |  | Create Project Proposal | Complete | Done | 9/21 - 9/28 | Amanda | Connor | Ethan | Jhet | Nathan
4 | / | Planning |  | Obtain Project Approval | Complete | Done | 9/21 - 9/28 | Jason Jenkins
5 | / | Planning |  | Select Development Methodology | Complete | Done | 9/21 - 9/28 | https://pickerwheel.com/ |  |  |  |  | democracy == gambling
6 | / | Planning |  | Check Requirements | Complete | Done | 9/24 - 9/28 |  | Connor
7 | / | Planning |  | Engine Familiarization | Active | High | 9/28 - 10/19 | Amanda | Connor | Ethan | Jhet | Nathan | Begin Phase 2 [EVERYTHING]
8 | / | Implementation / Design |  | Asset Design | Active | Normal | 10/12 - 10/23 | Amanda | Connor
9 | / | Implementation / Design |  | Sound Design | Active | Normal | 10/12 - 10/23 |  |  | Ethan | Jhet
10 | / | Implementation / Design |  | Level Design | Active | Normal | 10/12 - 10/30 |  | Connor |  | Ethan | Nathan
11 | / | Implementation / Design |  | AI Design | Active | Normal | 10/19 - 10/30 | Amanda |  |  | Jhet | Nathan
12 | / | Implementation / Design |  | Art Cohesion | Pending | Normal | 10/30 - 11/14 | Amanda | Connor | Ethan | Jhet | Nathan | Begin Phase 2.5 [KINTSUGI]
13 | / | Implementation / Design |  | Level Cohesion | Pending | Normal | 10/30 - 11/14 | Amanda | Connor | Ethan | Jhet | Nathan
14 | / | Implementation / Design |  | Entity Cohesion | Pending | Normal | 10/30 - 11/14 | Amanda | Connor | Ethan | Jhet | Nathan
15 | / | Testing |  | Holistic Playtesting | Pending | Low | 10/30 - 12/10 | Amanda | Connor | Ethan | Jhet | Nathan
16 | / | Testing |  | Outsourced Playtesting | Pending | Normal | 11/7 - 11/28 | to be determined
17 | / | Testing |  | Multiple OS Playtesting | Pending | Normal | 11-28 - 12/3 | Amanda | Connor | Ethan | Jhet | Nathan | one of us has a mac
18 | / | Deployment |  | Operation: Dropbox | Pending | High | 12/3 - 12/10 |  | Connor |  |  |  | Begin Phase 3 [PASSED THE CLASS]
19 | / | Analysis |  | Operation: Operation? | Pending | High | 12/3 - 12/10 | Amanda | Connor | Ethan | Jhet | Nathan
20 | / | Wrap-Up |  | Operation: Celebration | Pending | High :) | 12/3 - Beyond :) | Amanda | Connor | Ethan | Jhet | Nathan | pizza and beer
Project Roles
|  | 2D Asset Team | Amanda, Connor
|  | Sound Design Team | Ethan, Jhet
|  | Level Design Team | Connor, Ethan, Nathan
|  | AI Design Team | Amanda, Jhet, Nathan
|  | Programming Team | All
|  | Organizational Lead | Connor, Jhet
|  | Project Sponsor | Nathan